## PROJECT PROFILE
Defect Tracking Sheet
TMT/TD05/TMP
Project ID | PROJECT_PHP_01
Project Name | PHP Travels Website
Prepared/Modified by | Role | Date of Preparation
| Tester | 2018-01-11
Reviewed by | Role | Date of Review
SME
Approved by | Role | Date of Approval
Test Manager
Circulation List
Version Number | 1

## defect tracking
Project ID: PROJECT_PHP_01 |  | Project Name : PHP Travels Website
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments
DF_CARS_001 | CAR | The Pick Up Location and Drop off Location in Cars Page is found to accept the same Pick Up and Drop Off Location. | Detailed Description: The Pick Up Location and Drop off Location in Cars Page is found to accept the same Pick Up and Drop Off Location. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Cars option from the menu bar and fill all valid details except Pick Up and Drop off Location 4. Enter Pick Up Date 5. Enter Pick Up Time 6. Enter Drop Off Date 7. Enter Drop Off Time 8. Click on Search Button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts same Pick Up and Drop Off Location .The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1 | Build 1.0 | 2018-01-11 | Shubhangi Gurav |  | ACT | Test Cycle 1
DF_CARS_002 | CAR | The Pick Up Time and Drop off Time in Cars Page is found to accept the Time which have already elapsed. | Detailed Description: The Pick up Time and Drop Off Time in Cars Page is found to accept the Time which has already elapsed. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Cars option from the menu bar and fill all valid details except Pick Up and Drop off Time 4. Enter Pick Up Location 5. Enter Pick Up Date 6. Enter Drop Off Location 7. Enter Drop Off Date 8. Click on Search Button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts the Time which has already elapsed .The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | High | High | 1 | Build 1.0 | 2018-01-11 | Shubhangi Gurav |  | ACT | Test Cycle 1
DF_CARS_003 | PERSONAL DETAILS | The First Name field in Book as a Guest in Personal Details is found to accept any inputs rather than only alphabets | Detailed Description: The First Name field is found to accept any inputs other than only alphabets Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Cars option from the menu bar and fill all valid details and click on Book Now 4. Enter First Name 5. Enter Last Name 6. Enter Email 7. Enter Confirm Email 8. Enter Mobile Number 9.Enter Address 10.Select Country 11. Click on "Confirm this Booking" Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts invalid First Name.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | Low | Low | 1 | Build 1.0 | 2018-01-11 | xyz |  | ACT | Test Cycle 1
DF_CARS_004 | PERSONAL DETAILS | The Last Name field in Book as a Guest in Personal Details is found to accept any inputs rather than only alphabets | Detailed Description: The Last Name field is found to accept any inputs other than only alphabets Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Cars option from the menu bar and fill all valid details and click on Book Now 4. Enter First Name 5. Enter Last Name 6. Enter Email 7. Enter Confirm Email 8. Enter Mobile Number 9.Enter Address 10.Select Country 11. Click on "Confirm this Booking" Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also accepts invalid Last Name.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | Low | Low | 1 | Build 1.0 | 2018-01-11 | xyz |  | ACT | Test Cycle 1
DF_CARS_005 | PERSONAL DETAILS | The Mobile Number field in Book as a Guest in Personal Details is a mantory field but the booking is getting confirmed even after leaving the field blank. | Detailed Description:The Mobile Number field in Personal Details is a mantory field but the booking is getting confirmed even after leaving the field blank. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Cars option from the menu bar and fill all valid details and click on Book Now 4. Enter First Name 5. Enter Last Name 6. Enter Email 7. Enter Confirm Email 8. Enter Mobile Number 9.Enter Address 10.Select Country 11. Click on "Confirm this Booking" Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also blank Mobile Number.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | Low | Low | 1 | Build 1.0 | 2018-01-11 | xyz |  | ACT | Test Cycle 1
DF_CARS_006 | PERSONAL DETAILS | The Address field in Book as a Guest in Personal Details is a mantory field but the booking is getting confirmed even after leaving the field blank. | Detailed Description: The Address field in Personal Details is a mantory field but the booking is getting confirmed even after leaving the field blank. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Cars option from the menu bar and fill all valid details and click on Book Now 4. Enter First Name 5. Enter Last Name 6. Enter Email 7. Enter Confirm Email 8. Enter Mobile Number 9.Enter Address 10.Select Country 11. Click on "Confirm this Booking" Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credential fields but also blank Address.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | Low | Low | 1 | Build 1.0 | 2018-01-11 | xyz |  | ACT | Test Cycle 1
DF_CARS_007 | PERSONAL DETAILS | The Country field in Personal Details is a mantory field but the booking is getting confirmed even if the user is not selecting any of the country. | Detailed Description: The Country field in Personal Details is a mantory field but the booking is getting confirmed even if the user is not selecting any of the country. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Cars option from the menu bar and fill all valid details and click on Book Now 4. Enter First Name 5. Enter Last Name 6. Enter Email 7. Enter Confirm Email 8. Enter Mobile Number 9.Enter Address 10.Select Country 11. Click on "Confirm this Booking" Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credentials and also when no country is selected.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | Low | Low | 1 | Build 1.0 | 2018-01-11 | xyz |  | ACT | Test Cycle 1
DF_CARS_008 | PAYMENT METHOD | The card Number Field in Stripe Credit Card method is found to accept any data other than numbers. | Detailed Description:The card Number Field in Payment method of Invoice Page is found to accept any data other than numbers. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Cars option from the menu bar and fill all valid details and click on Book Now. 4. Click on "Confirm this Booking" 5. Enter First Name 6. Enter Last Name 7. Enter Card Number 8. Select Month 9.Select Year 10. Enter Card CVV 11. Click on "Pay Now" Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credentials and also invalid Card Number in Payment Method form.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | Low | Low | 1 | Build 1.0 | 2018-01-11 | xyz |  | ACT | Test Cycle 1
DF_CARS_009 | PAYMENT METHOD | The First Name Field in Payment Method of Stripe Credit Card is found to accept any data other than alphabets. | Detailed Description:The First Field in Payment method of Invoice Page is found to accept any data other than alphabets. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Cars option from the menu bar and fill all valid details and click on Book Now. 4. Click on "Confirm this Booking" 5. Enter First Name 6. Enter Last Name 7. Enter Card Number 8. Select Month 9.Select Year 10. Enter Card CVV 11. Click on "Pay Now" Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credentials and also invalid First Name in Payment Method form.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | Low | Low | 1 | Build 1.0 | 2018-01-11 | xyz |  | ACT | Test Cycle 1
DF_CARS_010 | PAYMENT METHOD | The Last Name Field in Payment Method of Stripe Credit Card is found to accept any data other than alphabets. | Detailed Description:The First Field in Payment method of Invoice Page is found to accept any data other than alphabets. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Cars option from the menu bar and fill all valid details and click on Book Now. 4. Click on "Confirm this Booking" 5. Enter First Name 6. Enter Last Name 7. Enter Card Number 8. Select Month 9.Select Year 10. Enter Card CVV 11. Click on "Pay Now" Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credentials and also invalid First Name in Payment Method form.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | Low | Low | 1 | Build 1.0 | 2018-01-11 | xyz |  | ACT | Test Cycle 1
DF_CARS_011 | PAYMENT METHOD | The required mandatory Card CVV Field in Payment Method of Stripe Credit Card is found to accept blank data. | Detailed Description:The required mandatory Card CVV Field in Payment Method of Stripe Credit Card is found to accept blank data. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Cars option from the menu bar and fill all valid details and click on Book Now. 4. Click on "Confirm this Booking" 5. Enter First Name 6. Enter Last Name 7. Enter Card Number 8. Select Month 9.Select Year 10. Enter Card CVV 11. Click on "Pay Now" Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credentials and also blank Card CVV in Payment Method form.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | Low | Low | 1 | Build 1.0 | 2018-01-11 | xyz |  | ACT | Test Cycle 1
DF_CARS_012 | PAYMENT METHOD | The required mandatory Card CVV Field in Payment Method of Stripe Credit Card is found to accept any type of inputs otherthan numbers. | Detailed Description:The required mandatory Card CVV Field in Payment Method of Stripe Credit Card is found to accept any type of inputs otherthan numbers. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Cars option from the menu bar and fill all valid details and click on Book Now. 4. Click on "Confirm this Booking" 5. Enter First Name 6. Enter Last Name 7. Enter Card Number 8. Select Month 9.Select Year 10. Enter Card CVV 11. Click on "Pay Now" Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credentials and also invalid Card CVV.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | Low | Low | 1 | Build 1.0 | 2018-01-11 | xyz |  | ACT | Test Cycle 1
DF_CARS_013 | PAYMENT METHOD | The card Number Field in Credit Card method is found to accept any data other than numbers. | Detailed Description:The card Number Field in Credit Card Payment method of Invoice Page is found to accept any data other than numbers. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Cars option from the menu bar and fill all valid details and click on Book Now. 4. Click on "Confirm this Booking" 5. Enter First Name 6. Enter Last Name 7. Enter Card Number 8. Select Month 9.Select Year 10. Enter Card CVV 11. Click on "Pay Now" Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credentials and also invalid Card Number in Payment Method form.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | Low | Low | 1 | Build 1.0 | 2018-01-11 | xyz |  | ACT | Test Cycle 1
DF_CARS_014 | PAYMENT METHOD | The First Name Field in Payment Method of Credit Card is found to accept any data other than alphabets. | Detailed Description:The First Field in Credit Card Payment method of Invoice Page is found to accept any data other than alphabets. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Cars option from the menu bar and fill all valid details and click on Book Now. 4. Click on "Confirm this Booking" 5. Enter First Name 6. Enter Last Name 7. Enter Card Number 8. Select Month 9.Select Year 10. Enter Card CVV 11. Click on "Pay Now" Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credentials and also invalid First Name in Payment Method form.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | Low | Low | 1 | Build 1.0 | 2018-01-11 | xyz |  | ACT | Test Cycle 1
DF_CARS_015 | PAYMENT METHOD | The Last Name Field in Payment Method of Credit Card is found to accept any data other than alphabets. | Detailed Description:The First Field in Credit Card Payment method of Invoice Page is found to accept any data other than alphabets. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Cars option from the menu bar and fill all valid details and click on Book Now. 4. Click on "Confirm this Booking" 5. Enter First Name 6. Enter Last Name 7. Enter Card Number 8. Select Month 9.Select Year 10. Enter Card CVV 11. Click on "Pay Now" Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credentials and also invalid First Name in Payment Method form.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | Low | Low | 1 | Build 1.0 | 2018-01-11 | xyz |  | ACT | Test Cycle 1
DF_CARS_016 | PAYMENT METHOD | The required mandatory Card CVV Field in Payment Method of Credit Card is found to accept blank data. | Detailed Description:The required mandatory Card CVV Field in Payment Method of Credit Card is found to accept blank data. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Cars option from the menu bar and fill all valid details and click on Book Now. 4. Click on "Confirm this Booking" 5. Enter First Name 6. Enter Last Name 7. Enter Card Number 8. Select Month 9.Select Year 10. Enter Card CVV 11. Click on "Pay Now" Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credentials and also blank Card CVV in Payment Method form.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | Low | Low | 1 | Build 1.0 | 2018-01-11 | xyz |  | ACT | Test Cycle 1
DF_CARS_017 | PAYMENT METHOD | The required mandatory Card CVV Field in Payment Method of Credit Card is found to accept any type of inputs otherthan numbers. | Detailed Description:The required mandatory Card CVV Field in Payment Method of Credit Card is found to accept any type of inputs otherthan numbers. Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Cars option from the menu bar and fill all valid details and click on Book Now. 4. Click on "Confirm this Booking" 5. Enter First Name 6. Enter Last Name 7. Enter Card Number 8. Select Month 9.Select Year 10. Enter Card CVV 11. Click on "Pay Now" Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the other credentials and also invalid Card CVV.The application proceeds to the next page.There is no error message shown as expected. | Coding | Google Chrome | Internal Dev | Low | Low | 1 | Build 1.0 | 2018-01-11 | xyz |  | ACT | Test Cycle 1
Note on A3: Alphy Chenganiyadan Give a unique number for the Defect Id
Note on B3: Alphy Chenganiyadan: Give the name of the module being tested
Note on C3: Alphy Chenganiyadan: Summarize the defect in 1 or 2 lines
Note on D3: Alphy Chenganiyadan: A detailed description of the defect
Note on E3: Alphy Chenganiyadan: Categorize the defect into the one of the values given in the drop down list
Note on F3: Alphy Chenganiyadan: Mention the name of the browser the defect was found in.
Note on G3: Alphy Chenganiyadan: Mention the environment in which the defect was found.
Note on H3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I3: Prioritize the defect
Note on J3: Alphy Chenganiyadan: Enter the Release # in which the defect was detected.
Note on K3: Alphy Chenganiyadan: Enter the Build # in which the defect was detected.
Note on L3: Alphy Chenganiyadan: Mention the date the defect was reported
Note on M3: Alphy Chenganiyadan: Name of the person who reported the defect.
Note on N3: Alphy Chenganiyadan: Name of the person the defect is assigned to.
Note on O3: Alphy Chenganiyadan: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P3: Alphy Chenganiyadan: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q3: Alphy Chenganiyadan: Mention the Test Case No that the defect was found while testing
Note on R3: Alphy Chenganiyadan: Name of the person who fixed the defect.
Note on S3: Alphy Chenganiyadan: Mention the date the defect was Fixed
Note on T3: Alphy Chenganiyadan: Mention the date the defect was verified
Note on U3: Alphy Chenganiyadan: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V3: Alphy Chenganiyadan: Enter the Release # in which the defect was available for verification
Note on W3: Alphy Chenganiyadan: Enter the Build # in which the defect was available for verification
Note on X3: Alphy Chenganiyadan: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y3: Alphy Chenganiyadan: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.